## Project Progress
PROJECT CHARTER - PROGRESS TRACKER
CUSTOMER SESSION PORTAL
Weeks | Entry Filled by | Expected outcome | Actual Completion | Stage of the project charter | % of completion | Challenges (If any)
Week-1 |  |  |  |  | 25%
Week-2 |  |  |  |  | 50%
Week-3 |  |  |  |  | 75%
Week-4 |  |  |  |  | 100%
Week-5
Note on B3: Priyadharshini Vivekanandan Gopal: Name of the person, updating the field
Note on C3: Priyadharshini Vivekanandan Gopal: Discuss with your mentor and update the no.of task to be completed for the particular week
Note on D3: Priyadharshini Vivekanandan Gopal: Before Every Monday - actual completion of task to be mention
Note on E3: Priyadharshini Vivekanandan Gopal: Please update the current stage of your project. For your reference below mentioned are stages for project charter (i.e., 1.Requirement Gathering 2. Data Cleaning and Processing 3. Front-end Design/back End Design 4. APIs Design 5. Authentication and Authorization 6. Data Storage 7. Testing and Deployment 8.Continuous Integration/Continuous Deployment (CI/CD)
Note on F3: Priyadharshini Vivekanandan Gopal: Please fill your curren week % of completion

## UI Dev Tracker
| CUSTOMER SESSION MANAGEMENT |  |  |  |  | Software Tools Required |  |  | UI Team
[6 empty] | Vs Code |  |  | Durgam Prashanth
[6 empty] | Node.js v14+ |  |  | Sunit Kumar Pattnaik ,
[6 empty] | Angular CLI v15+ |  |  | Ruchika A G S,
[6 empty] | Postman |  |  | Saikiran Achari
SN | User Story | Acceptance Criteria | Start Date | End Date | Developer | Support Links | Status | Dependancy
1 | Create Basic Angular Application | 1-Angular v15 must use 2-Configure unit test using jest framework 3-Eslint should be integrated(static code analysing tool), basic eslint rules should be added. 4-Angular material UI library should be installed 5-Basic application layout should be available. 6- Integrate bootstrap in the application. 7- Application should be complete responsive. 8- No errors in browser console 9-All the basic scripts should be added in the application package.json 10- Basic folder structures should be created | 2023-08-03 | 2023-08-04 |  | 1-https://angular.io/quick-start 2-https://medium.com/@kyjungok/setup-jest-in-angular-application-22b22609cbcd 3-https://javascript.plainenglish.io/how-to-configure-eslint-and-prettier-on-angular-application-87dbd767369c | Not Started | NA,
2 | Application Header | 1-Create application header with proper height and background color 2- Display application name with proper logo in top left of the header 3- Display user logo at right side of header. 4- Once the user logged in display logged in username along with user logo. 5-Click on user logo will display dropdown menu with login option if not logged in , logout option if already logged in. 6- Header should be completely responsive. |  |  |  | 1-https://getbootstrap.com/docs/4.0/components/navbar/? 2-https://www.truecodex.com/course/angular-material/angular-material-sidenav-and-toolbar-example |  | NA
3 | User Login Page | 1- Create responsive login component / screen based on UX 2- Login page should contain the following fields ( username,password,login button) 3-UI validation with proper error messages (error message if not provided proper input in username password fields) 4-Create/call method for login when user click on login button. 5-Unit test should be written for login method with 90% coverage. 6- Create separate service for login (LoginService) along with unit test. | [5 empty] | Login API
4 | Dashboard | 1-Create new Dashboard component 2-Once the login is success route the application from login screen into dashboard screen. 3-show some loader when until we get response from active/archive session api. 4-Create Dashboard layout as per UX mock design provided. 5-Implement Active and Archived tabs in table as per design.
5 | Create Session Popup | 1-Create the create session popup with required fields 2- Use UI validation for all the input fields 3- Enable the create session button only after UI validation is success 4- Show some UI loader inside the popup until we get the success response from create-session api and once the response is success close the dialog, else show message to user :" Failed to create the session!"
6 | Edit Session Popup | 1- Create the Edit session popup as per design. 2- Pre-populate the field values in edit table when you click edit option from dashboard table. 3-Enable the edit button if any field values are changed. 4-Show some loader in popup when you click on edit button and dismiss the loader once the item is updated successfully(success api response). 5-Show error message in footer of popup if edit api is failed.
7 | View Session Popup | 1- Create view popup with required fields as per UX design. 2-All the fields are read only . 3-When click on view button from dashboard table pass specific row data from dashboard component to view component. 4-Clicking outside / close button in dislog will dismiss the popup.
8 | Delete Session Popup
9 | Login API Integration
10 | Active / Archive Session API Integration
11 | Edit Session API Integration
12 | Delete Session API Integration
13 | Implement Logout functionality
14
15
16

## Doubts
Doubt | Solution
Is the sessionId confidential? If not, then can we pass it in the url like -> PATCH http://localhost:8080/api/sessions/archive/{SessionID} | nothing will be passing using url | eg: {sessionId: 234234}
Is remarks field same as the notes mentioned in the project charter? Is it like a short part of notes that we display on the dashboard and when the RM views the session we display the whole note? | Yes, Need to display entire notes when we use view session popup...
Is the relationship between RM and sessions one to many or many to many? Can an RM see the sessions of other RMs or he can see his own sessions? If RM can see his own sessions only, then is updatedBy field required? Are we assuming that some external entity(superuser) can update the session? | Its cannot be accessible.
Can a customer have only one active session or can he belong to multiple active sessions? | Multiple
Can we have a deletedOn field in history table instead of updatedBy / updatedOn ? | ?
When viewing the session, should it be in modal view or different page view? | Popup